## Sprint 1 Test Cases
TC_ID | US_ID | Test Scenario | Preconditions | Test Steps | Expected Result | Type | Automated Test | Executed | Status
TC_01 | US_01 | Enroll an agent with valid details | Backend running; agent name not used | 1. Send an enrollment request with all required fields. 2. Open the registry. | Agent is created with a unique ID and Active status and appears in the registry. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc01_enroll_agent_with_valid_details | 2026-10-18 | Pass
TC_02 | US_01 | Enroll with a missing required field | Backend running | 1. Send an enrollment request without capabilities. | Request is rejected with a validation error naming the field; no agent is created. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc02_enroll_with_missing_required_field, test_tc02_empty_capability_list_is_rejected | 2026-10-18 | Pass
TC_03 | US_01 | Enroll a duplicate agent name | An agent with this name exists | 1. Enroll another agent with the same name. | Request is rejected with a duplicate-name error; the original agent is unchanged. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc03_enroll_duplicate_agent_name, test_tc03_builtin_names_are_also_protected | 2026-10-18 | Pass
TC_04 | US_01 | Enrollment speed and single request | Backend running | 1. Enroll 10 agents one after another and time each request. | Each enrollment finishes in a single request in under 3 seconds with no duplicates. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc04_enrollment_is_a_single_fast_request | 2026-10-18 | Pass
TC_05 | US_01 | Disable an enrolled agent | An active agent exists | 1. Disable the agent. 2. Submit a brief that would need it. | The disabled agent is not spawned and is not offered to the orchestrator. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc05_disabled_agent_is_never_spawned | 2026-10-18 | Pass
TC_06 | US_02 | Brief needing several capabilities | Registry has at least 5 agents | 1. Submit: audit this code, fix critical issues, write tests, produce a report. | Multiple agents are spawned, each with its own instance ID and status; unrelated agents are skipped. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc06_brief_needing_several_capabilities | 2026-10-18 | Pass
TC_07 | US_02 | Brief needing one capability | Registry has at least 5 agents | 1. Submit: clean this CSV file. | Only the data cleaner is spawned; all others are skipped with a reason. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc07_brief_needing_one_capability | 2026-10-18 | Pass
TC_08 | US_02 | Brief with no matching agent | Registry has no agent for the capability | 1. Submit a brief asking for a capability nobody offers. | No agent is spawned and the user is told which capability is missing. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc08_brief_with_no_matching_agent | 2026-10-18 | Pass
TC_09 | US_02 | Empty or vague brief | Workspace open | 1. Submit an empty brief. 2. Submit: help me. | Empty brief is blocked; vague brief gets a clarifying question; no agents are spawned. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc09_empty_brief_is_blocked, test_tc09_vague_brief_gets_a_clarifying_question | 2026-10-18 | Pass
TC_10 | US_02 | Same brief submitted twice | Registry seeded | 1. Submit the same brief two times. | Two separate sets of agent instances are created with different IDs and no data collision. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc10_same_brief_twice_creates_separate_instances | 2026-10-18 | Pass
TC_11 | US_02 | Selection reason is shown | Brief submitted | 1. Open the spawn result for a brief. | Each spawned agent shows why it was selected; each skipped agent shows why it was skipped. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc11_selection_reason_is_shown | 2026-10-18 | Pass
TC_12 | US_03 | Table created on enrollment | Agent with a defined output schema | 1. Enroll the agent. 2. Inspect the database. | A table exists with columns and data types matching the output schema. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc12_table_created_on_enrollment | 2026-10-18 | Pass
TC_13 | US_03 | Unsafe table name | Backend running | 1. Enroll an agent named with SQL text, for example x; DROP TABLE users. | Name is rejected or sanitised; no SQL runs and existing tables are untouched. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc13_unsafe_table_name_is_sanitised, test_tc13_unsafe_property_names_are_rejected | 2026-10-18 | Pass
TC_14 | US_03 | Repeat table creation | Agent already enrolled with a table | 1. Trigger table creation again for the same agent. | No error and no duplicate table; existing data is kept. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc14_repeat_table_creation_keeps_data, test_tc14_new_schema_fields_add_columns | 2026-10-18 | Pass
TC_15 | US_03 | Table creation failure rolls back enrollment | Database set to fail on table creation | 1. Enroll an agent while table creation fails. | Enrollment returns an error and no partial agent record remains in the registry. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc15_table_creation_failure_rolls_back_enrollment | 2026-10-18 | Pass
TC_16 | US_04 | Reject a malformed schema | Backend running | 1. Enroll an agent whose schema is invalid JSON or has an unknown type. | Enrollment is rejected with an error naming the problem field. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc16_invalid_json_is_rejected, test_tc16_unknown_schema_type_is_rejected_naming_the_field, test_tc16_non_object_output_schema_is_rejected | 2026-10-18 | Pass
TC_17 | US_04 | Store valid agent output | Enrolled agent with a table | 1. Send output that matches the schema. | Output passes validation and is written to the agent's table. | Positive | backend/tests/test_sprint1_acceptance.py::test_tc17_valid_output_is_written_to_the_agent_table | 2026-10-18 | Pass
TC_18 | US_04 | Output with a missing required field | Enrolled agent with a table | 1. Send output missing a required field. | Output is rejected, the step is marked Failed, nothing is stored, and the error is logged with agent ID and field. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc18_output_missing_a_required_field | 2026-10-18 | Pass
TC_19 | US_04 | Output with the wrong data type | Enrolled agent with a table | 1. Send a text value where a number is required. | Output is rejected and the error names the field and expected type. | Negative | backend/tests/test_sprint1_acceptance.py::test_tc19_output_with_the_wrong_data_type | 2026-10-18 | Pass
TC_20 | US_05 | Submit a brief from the UI | Frontend and backend running | 1. Open /office. 2. Enter a multi-step brief. 3. Submit. | Spawned agents appear with status and selection reason. | Positive | frontend/e2e/sprint1.spec.ts "TC_20" | 2026-10-18 | Pass
TC_21 | US_05 | Empty brief blocked in the UI | Frontend running | 1. Click submit with an empty brief box. | Submission is blocked and a validation message is shown. | Negative | frontend/e2e/sprint1.spec.ts "TC_21" | 2026-10-18 | Pass
TC_22 | US_05 | Agents page matches the API | Several agents enrolled | 1. Open the agents page. 2. Compare with the list-agents API. | The same agents, capabilities and statuses are shown. | Positive | frontend/e2e/sprint1.spec.ts "TC_22" | 2026-10-18 | Pass
TC_23 | US_05 | Backend error shown to the user | Backend returns a validation error | 1. Trigger a rejected enrollment or brief from the UI. | A clear error message is shown and the page stays usable. | Negative | frontend/e2e/sprint1.spec.ts "TC_23" | 2026-10-18 | Pass
All 23 test cases passed in CI on 2026-10-18. CI workflow: https://github.com/htmw/F2026-T2-Phoenix/actions/workflows/ci.yml